## 30-Day Calendar
Day | Date | Weekday | Phase | Primary action | Deliverable | Owner | Dependency | Evidence / acceptance
1 | 2026-08-21 | Friday | Emergency compliance | Create a site-wide P0 patch: remove the internal-only UK contact from the live shell and scan all public files. | Corrected header/footer patch plus literal contact scan log. | PP-WEBDEV v2.0 | Management approval and production access | No prohibited contact pattern in release files.
2 | 2026-08-22 | Saturday | Emergency compliance | Deploy the approved contact patch in a controlled maintenance window; purge page/CDN cache. | Production release record and homepage/header/footer screenshots. | Human deployer + PP-WEBDEV | Day 1 patch approved | Live homepage and shared shell expose only the approved Pakistan contact.
3 | 2026-08-23 | Sunday | Emergency compliance | Run a crawl smoke test after the contact release; check home, blog, destinations, legal and profile-review pages. | Post-release crawl checklist. | PP-WEBDEV | Day 2 deployment | No recurrence across sampled live URLs; no broken shell assets.
4 | 2026-08-24 | Monday | Homepage trust repair | Patch live homepage team, partnership and outcome wording; replace “Partner Universities” with “University Network”; remove outcome-probability language. | Claim-checked homepage HTML and deployment notes. | PP-WEBDEV + Management | Approved replacement copy | Homepage passes contact, team, partnership and outcome-claim gates.
5 | 2026-08-25 | Tuesday | Crawl hygiene | Remove the crawler-visible blog empty-state and manual card template from public blog.html; keep the reusable template outside the public index. | Clean blog index with one real card only. | PP-WEBDEV | A1 remains live | No ARTICLE_TITLE, CATEGORY, “articles are being prepared,” or template tokens in fetched blog text.
6 | 2026-08-26 | Wednesday | Indexation | Rebuild sitemap from the real canonical inventory: destination hub, four country pages, legal pages, FAQ, blog and A1. Check canonicals and one-H1 status. | Validated sitemap.xml and URL inventory. | PP-WEBDEV | All target URLs return a publishable response | Every live canonical page appears once; no template/staging URLs.
7 | 2026-08-27 | Thursday | Measurement baseline | Confirm Search Console ownership, GA4 decision and conversion-event contract. Keep tracker blank if approval/ID is absent. | Baseline measurement sheet and access/dependency log. | Management + PP-WEBDEV | Management account access | GSC baseline recorded; analytics status explicitly configured or documented as inactive.
8 | 2026-08-28 | Friday | Destination cluster | Audit the four country pages for canonical, H1, reviewed date, official-source coverage, schema and internal links. | Country-page issue register. | PP-WEBDEV visibility-first | Live country pages | One exact patch list per country, prioritised P0–P2.
9 | 2026-08-29 | Saturday | A1 distribution | Prepare an approved A1 distribution pack: GBP excerpt, LinkedIn/Facebook summary, Instagram carousel copy and X answer capsule. | A1 social/GBP copy pack; no new factual claims. | PP-WEBDEV + Management | A1 source/status review | Every excerpt links to A1 and preserves indicative labels/caveats.
10 | 2026-08-30 | Sunday | Editorial QA | Run official-source and date-label review on destination-page figures; quarantine claims that cannot be re-verified. | Figure/source quarantine register. | PP-WEBDEV | Current official links and approved data | Every retained changeable figure has source/date/indicative framing.
11 | 2026-08-31 | Monday | UK page repair | Apply the UK page patch: semantic H1/heading review, source links, answer capsule, schema parity and internal links. | Claim-checked UK page release. | PP-WEBDEV + Human deployer | Day 8 audit; management approval | UK page passes claim, source, schema, link and mobile checks.
12 | 2026-09-01 | Tuesday | Ireland page repair | Apply the Ireland page patch: remove unsupported generalisations, verify finance/intake figures and add official answer capsules. | Claim-checked Ireland page release. | PP-WEBDEV + Human deployer | Day 8 audit; current official sources | Ireland page passes claim, source, schema, link and mobile checks.
13 | 2026-09-02 | Wednesday | Malaysia page repair | Apply the Malaysia page patch: qualify branch-campus/recognition claims, verify EMGS/work/cost statements and source register figures. | Claim-checked Malaysia page release. | PP-WEBDEV + Human deployer | Day 8 audit; current official sources | Malaysia page passes claim, source, schema, link and mobile checks.
14 | 2026-09-03 | Thursday | Turkey page repair | Apply the Turkey page patch: remove unsupported superlatives/probability language, verify Burslari/work/fee claims and link A1 bidirectionally. | Claim-checked Turkey page release and cluster link map. | PP-WEBDEV + Human deployer | Day 8 audit; current official sources | Turkey page and A1 link to each other; no unsupported outcome or acceptance-rate wording.
15 | 2026-09-04 | Friday | A2 approval gate | Receive the approved A2 Malaysia-fees copy deck; re-check every RM/PKR figure and source within 30 days. Do not build without the deck. | Approved A2 source ledger and build-ready deck. | Pathfinder/Management + PP-WEBDEV | Approved A2 Markdown copy deck | No unresolved figure; publication date remains unset until release.
16 | 2026-09-05 | Saturday | A2 production preparation | Prepare A2 card, metadata, schema inputs, tables and distribution snippets without publishing on the closed-office day. | A2 release candidate and QA checklist. | PP-WEBDEV | Day 15 approval | No placeholders; all schema text matches visible draft.
17 | 2026-09-06 | Sunday | A2 release queue | Run no-JS, mobile, print, link and schema tests; queue Monday release rather than inventing a weekend service response. | Signed A2 release checklist. | PP-WEBDEV + Management | A2 release candidate | All release gates passed or blocker logged.
18 | 2026-09-07 | Monday | A2 publish | Publish A2, update featured/latest cards and sitemap, request indexing, and release approved GBP/social excerpts. | Live A2 URL, sitemap entry and distribution record. | Human deployer + PP-WEBDEV | Day 17 release approval | A2 returns 200, is canonical, linked and included once in sitemap.
19 | 2026-09-08 | Tuesday | A3 approval gate | Receive the approved A3 PTE-vs-IELTS deck; verify destination-by-destination acceptance notes against current institution/official information. | A3 acceptance matrix and approved deck. | Pathfinder/Management + PP-WEBDEV | Approved A3 Markdown copy deck | Each acceptance statement is dated, scoped and non-universal.
20 | 2026-09-09 | Wednesday | A3 build | Build A3 with comparison table, answer capsules, FAQ parity, source block and CTA events. | Self-contained A3 release candidate plus guide. | PP-WEBDEV | Day 19 approved deck | Article template contract and ≤350KB budget pass.
21 | 2026-09-10 | Thursday | A3 publish | Publish A3; update blog index, sitemap, related links and approved social/GBP distribution. | Live A3 URL and release record. | Human deployer + PP-WEBDEV | A3 management approval | A3 returns 200, is canonical and linked from relevant country pages.
22 | 2026-09-11 | Friday | AEO retrofit | Audit A1–A3 and destination pages for genuine 40–60-word answer capsules, definitions, FAQ parity and table extractability. | AEO question-to-capsule map and implemented safe patches. | PP-WEBDEV visibility-first | A1–A3 live or blockers documented | No schema-only FAQ; answer capsules preserve caveats.
23 | 2026-09-12 | Saturday | Performance & accessibility | Run automated and manual 360/768/1440, keyboard, reduced-motion, print and file-size checks on the blog/destination cluster. | Accessibility/performance issue log. | PP-WEBDEV | Current production files | No P0 accessibility defect; article pages remain within the governed size budget.
24 | 2026-09-13 | Sunday | Local entity desk audit | Compare website NAP, GBP name/address/hours, social profiles and approved directory citations. Prepare corrections without publishing on the closed-office day. | NAP/entity consistency worksheet. | PP-WEBDEV visibility-first + Management | GBP and profile access | One approved entity string used everywhere; no internal contact/location leakage.
25 | 2026-09-14 | Monday | Local visibility | Apply approved GBP/profile/citation corrections and publish one useful, non-promotional GBP Q&A/post linking to the strongest live guide. | GBP/entity update log. | Management + PP-WEBDEV | Day 24 approvals | Public profiles match the entity registry; no incentivised review activity.
26 | 2026-09-15 | Tuesday | LLMO assets | Create review-stage llms.txt and llms-full.txt from canonical, citable pages; include data-policy and four-destination scope. | Root AI-discovery files ready for approval. | PP-WEBDEV visibility-first | Canonical inventory stable | No unpublished, broken or non-canonical URL in either file.
27 | 2026-09-16 | Wednesday | Crawler governance | Review robots.txt and prepare deliberate AI-crawler policy; publish only after management approves. | Validated robots.txt patch and quarterly review date. | PP-WEBDEV + Management | Crawler-policy decision | Robots remains crawlable for search; policy is documented, not accidental.
28 | 2026-09-17 | Thursday | Submission & discovery | Submit final sitemap in GSC; configure IndexNow/Bing if credentials are approved; request indexing for newly published URLs. | Submission log with timestamps. | Management + PP-WEBDEV | GSC/Bing access | Each new canonical URL submitted once; no staging/template URL submitted.
29 | 2026-09-18 | Friday | AI visibility baseline | Run the fixed visibility prompt battery across approved engines and log brand presence, cited URLs and sentiment without claiming causation. | ai_visibility_log.csv baseline and one-page findings. | PP-WEBDEV visibility-first | Approved access/manual probe process | A reproducible baseline exists for next month.
30 | 2026-09-19 | Saturday | Monthly review | Publish the 30-day report: completed fixes, indexed URLs, impressions/clicks if available, conversions, AI-citation baseline, blockers and next 30-day plan. | Management one-pager and next calendar. | PP-WEBDEV + Management | Days 1–29 evidence | Every KPI is sourced; no ranking or conversion claim without data.

## Issue Register
ID | Severity | Evidence | Exact fix | Owner | Target | URL/evidence
VIS-001 | P0 | Live homepage exposes the internal-only UK contact in the top bar. | Remove it from shared header/footer and every public file; purge caches; re-crawl. | PP-WEBDEV + human deployer | Days 1–3 | https://pathplaza.com/
VIS-002 | P0 | Homepage contains team-capacity, “Partner Universities,” scholarship-probability and “smooth visa approval” wording. | Ship approved singular/channel/outcome-safe replacements before further promotion. | PP-WEBDEV + Management | Day 4 | https://pathplaza.com/
VIS-003 | P1 | Fetched blog text exposes the hidden empty-state and manual template tokens such as ARTICLE TITLE and CATEGORY. | Remove template/empty inventory from public blog.html; store templates only in the governed workspace. | PP-WEBDEV | Day 5 | https://pathplaza.com/blog.html
VIS-004 | P1 | Live sitemap includes the core seven pages and blog URLs but omits the destination hub, four country pages and additional legal/FAQ pages. | Rebuild sitemap from the live canonical inventory and validate XML. | PP-WEBDEV | Day 6 | https://pathplaza.com/sitemap.xml
VIS-005 | P1 | Country pages are live with numerous dated figures and some unsupported superlatives, behavioural claims or broad acceptance/work statements. | Run country-by-country claim/source quarantine and publish exact patches. | PP-WEBDEV + Management | Days 8–14 | /study-in-{uk,ireland,malaysia,turkey}.html
VIS-006 | P1 | Live destination/blog fetches expose Cloudflare-obfuscated email rather than the required plain-text mailto representation to non-JS readers. | Disable email obfuscation for the approved public email or render a crawlable plain-text equivalent. | PP-WEBDEV + human deployer | Days 3–6 | https://pathplaza.com/destinations.html
VIS-007 | P2 | Page shells are inconsistent across legacy, destination and blog files, increasing compliance drift. | Create one compliant shell contract and migrate pages through tested patches. | PP-WEBDEV | Days 4–14 | Live page comparison
VIS-008 | P2 | robots.txt is clean but has no deliberate AI-crawler policy; llms.txt and llms-full.txt are absent. | Draft AI policy and LLM discovery files; publish after approval. | PP-WEBDEV + Management | Days 26–27 | https://pathplaza.com/robots.txt
VIS-009 | P2 | GA4 remains unconfigured in current builds and GSC reporting access is not confirmed. | Document baseline access; activate only approved IDs and test events. | Management + PP-WEBDEV | Day 7 | Workspace GA4 placeholder
VIS-010 | P2 | A1 has a source-status dependency for the Turkish Embassy Islamabad hostname and requires publish-day source checks. | Verify or replace with the current official mission page; log checked date. | PP-WEBDEV | Days 8–10 | A1 deployment guide
VIS-011 | P2 | Homepage still hotlinks an Unsplash image, contrary to the production media policy. | Replace with approved local compressed media with dimensions and suitable alt text. | PP-WEBDEV + Management | Day 4 | https://pathplaza.com/
VIS-012 | P3 | Local/entity consistency and AI-citation presence have no recorded baseline. | Complete NAP/GBP audit and establish a repeatable AI-visibility probe log. | PP-WEBDEV visibility-first + Management | Days 24–29 | No current workspace log

## Milestones
ID | Date | Milestone | Acceptance condition
M1 | 2026-08-23 | Safety baseline | Internal-only contact removed live; post-release crawl clean.
M2 | 2026-08-27 | Crawl and measurement baseline | Homepage claims patched; public blog template removed; full sitemap submitted; GSC/GA4 status known.
M3 | 2026-09-03 | Destination cluster repaired | Four country pages claim/source/schema checked and bidirectionally linked.
M4 | 2026-09-10 | Phase-A content cluster | A1 plus A2/A3 live only if approved decks and source ledgers pass.
M5 | 2026-09-19 | Visibility operating system | AEO retrofit, entity audit, LLM files/policy review, discovery submissions and AI probe baseline complete.

## Content Plan
Asset | Working title | Primary keyword | Target URL | Target date | Status/dependency | Cluster
A1 | Turkey Student Visa: A Document Checklist for Pakistani Applicants (2026) | turkey student visa pakistan documents | /blog/turkey-student-visa-documents-pakistan.html | 2026-08-21 | Live; immediate crawl/source cleanup | Turkey / Process & Visa Files
A2 | Malaysia University Fees Explained: What Your Family Will Actually Pay in 2026 | malaysia university fees pakistani students | /blog/malaysia-university-fees-pakistani-students-2026.html | 2026-09-07 | Conditional on approved copy deck and fresh figures | Malaysia / Money & Scholarships
A3 | PTE vs IELTS in 2026: Which Test for UK, Ireland, Malaysia & Turkey? | pte vs ielts 2026 | /blog/pte-vs-ielts-2026-which-test.html | 2026-09-10 | Conditional on approved copy deck and acceptance matrix | Process & Visa Files
B1 brief | UK January 2027 Intake Deadlines for Pakistani Students | uk january 2027 intake deadline pakistan | TBD after brief approval | 2026-09-18 | Content brief only; publish in next cycle | UK / Process

## KPI Framework
Measure | Current baseline | Day-30 operating target | Evidence source
Internal-only public contact exposure | Present on live homepage | Zero verified instances | Literal crawl/grep
Indexable placeholders/template text | Present in fetched blog output | Zero | Fetched HTML/text check
Sitemap coverage | Incomplete | Every live canonical URL included once | Validated sitemap inventory
Country pages | Four live; audit status incomplete | Four claim/source/schema checked | Release QA logs
Live blog posts | 1 | Up to 3, conditional on approved copy decks | Live 200 URL + sitemap
Official sources per YMYL-adjacent article | A1 has multiple links | At least 2 checked official sources per article | Source ledger
GSC and GA4 baseline | Unknown/unconfigured | Access/status documented; approved events tested if configured | GSC/GA4 record
LLM discovery files | Absent | Drafted and published only if approved | Root-file check
AI visibility baseline | Not logged | One reproducible prompt-battery baseline | ai_visibility_log.csv
Ranking outcome | No reliable baseline | Observe only; no 30-day ranking promise | GSC and manual SERP review